## README
Risk register: VitaClin (fictitious)
Scores and levels are calculated automatically. Target for week 6: 20 risks covering privacy, security, third parties, continuity and regulation (LGPD, GDPR, NIS2 context).
Blue row = fictitious example.

## Risk register
ID | Risk description (cause, event, consequence) | Asset / process | Threat | Vulnerability | Owner | Probability (1-5) | Impact (1-5) | Inherent score | Inherent level | Treatment (mitigate / accept / transfer / avoid) | Controls (ISO/IEC 27002) | Action plan | Due date | Residual probability | Residual impact | Residual score | Residual level | Status
R-01 | Weak access control to health records leads to unauthorised access to sensitive patient data, causing harm to patients and regulatory sanctions | Electronic health record | Credential theft | No MFA for clinic users; no periodic access review | CTO | 4 | 5 |  |  | Mitigate | 5.15, 5.18, 8.5 | Enforce MFA; quarterly access review; alert on anomalous access | YYYY-MM-DD | 2 | 5 |  |  | Open

## Method
Scale | Meaning
Probability 1 | Rare: not expected in the next 3 years
Probability 3 | Possible: could happen once a year
Probability 5 | Almost certain: expected several times a year
Impact 1 | Negligible: no effect on data subjects or operations
Impact 3 | Moderate: limited data exposure, short downtime, possible complaint
Impact 5 | Severe: sensitive data exposed at scale, regulatory sanction, long downtime
Score | Probability x Impact (1 to 25)
Level | High >= 15; Medium 8 to 14; Low <= 7
Method | Based on ISO 31000 and ISO/IEC 27005: identify, analyse, evaluate, treat, monitor